## Sheet1
Project name |  | Evershop | TC Start Date | 18/10/2025 |  |  | TEST CASE
Module Name |  | Search | TC End Date | 18/10/2025 |  |  | PASS | 4
|  |  | Test Case Developed By | Amin Ocin |  |  | FAIL | 6
Developer Name (TL) |  |  | Test Case Reviewed By |  |  |  | Total | 10
Test_Case_ID |  | Section | Test Scenario | Preconditions | Test Steps | Input Data | Expected Outcome | Actual outcome | Status | Test Environment | Priority | Bug Report
TC_01 | Funtionality Test | Search | Verify that system shows message for no matched result | 1. Navigate to the log in site | 1. Navigate to the log in site. 2. Search with random string | yz123 | Shows "there is no product to display" message | shows the exact message | Passed | https://demo.evershop.io/ | High
TC_02 |  |  | Verify that the search can handle typo | 1. Navigate to the log in site | 1. Navigate to the log in site. 2. Search with typo | Nikee | Shows same output as nike | Does not show any product | Failed | https://demo.evershop.io/ | High | Sheet3, Cell D3
TC_03 |  |  | Verifythat search suggest Product based on typing | 1. Navigate to the log in site | 1. Navigate to the log in site. 2. Search with products name 3. Check for highlited words | Nik | Should suggesst product with 'nike' while typing | Does not suggest | Failed | https://demo.evershop.io/ | High | Sheet3, Cell B3
TC_04 |  |  | Verify that user can paste coppied words in search | 1. Navigate to the log in site | 1.Navigate to the log in site 2. paste a coppied word in the search | Nike Zoom | Should be able to paste coppied words | Able to paste | Passed | https://demo.evershop.io/ | Medium
TC_05 |  |  | Verify that the typed keyword is highlighted in the search suggestions | 1. Navigate to the log in site | 1.Navigate to the log in site 2. write keywords in th search | Nike React | Should highlight the keywords | Doess not highlight | Failed | https://demo.evershop.io/ | Medium | Sheet3, Cell F3
TC_06 | log in |  | verify that the search feature has search icon | 1. Navigate to the log in site | 1.Navigate to the log in site 2.Check the search icon | N/A | should have the search icon | Has the icon | Passed | https://demo.evershop.io/ | Medium
TC_07 |  |  | Verify that the search icon is palced at the top | 1. Navigate to the log in site | 1.Navigate to the log in site 2.Check the search icon | N/A | should be placed at the top | placed at the top | Passed | https://demo.evershop.io/ | Low
TC_08 |  |  | Verify that the search icon shows 'search' while hovering on it | 1. Navigate to the log in site | 1.Navigate to the log in site 2.Hover on top of the search icon | N/A | Should show 'search' while hoverring | Does not show anything while hovering | Failed | https://demo.evershop.io/ | Low | Sheet3, Cell B18
TC_09 |  |  | Verify that the search dropdown shows recent searchess | 1. Navigate to the log in site | 1.Navigate to the log in site 2. click on the search icon 3. check for recent searches | N/A | Should show the recent searches | Does not show anything in the dropdown | Failed | https://demo.evershop.io/ | Medium | Sheet3, Cell D18
TC_10 |  |  | verify that the voice input is present in the search option | 1. Navigate to the log in site | 1.Navigate to the log in site 2. click on the search icon 3. check for the voice search | N/A | Should be peresent | voice input is not present | Failed | https://demo.evershop.io/ | Medium | Sheet3, Cell F18

## Sheet2
Test Case Report
Project Name | Evershop
Module Name | Search
Test Case Version | v1
Written By | Amin Ocin
Executed By | Amin Ocin
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS |  | FAIL |  | Not Executed | Out Of Scope | Total TC
Individual Count | Functionality | UI | Functionality | UI | 0 | 0 | 10
| 2 | 2 | 3 | 3
Grand Total | 4 |  | 6 |  | 0 | 0 | 10

## Sheet3
Bug Reporting | Bug Reporting | Bug Reporting
# TC_ID 2 | # TC_ID 3 | # TC_ID 5
Issue: Unable to handle misspelling and show highest matched products | Issue: Does not suggest produts while typing the searched products | Issue: Unable to Highlight the keywords while typing
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Navigate to the log in site. 2. Search with a misspeling | 1. Navigate to the log in site. 2. Search with products name. 3. Check for suggestion | 1. Navigate to the log in site. 2. Search with products name. 3. Check for highlited words
Module: Search | Module: Search | Module: Search
Priority: HIgh | Priority: HIgh | Priority: Medium
Screenshot: Can't Handle misspelling | Screenshot: Does not suggest product while typing | Screenshot: Does not highlight the keywords
Responsible QA: Amin Ocin | Responsible QA: Amin Ocin | Responsible QA: Amin Ocin
Bug Reporting | Bug Reporting | Bug Reporting
# TC_ID 8 | # TC_ID 9 | # TC_ID 10
Issue: Does not show 'search'while hoveringon the search icon | Issue: Does not show recent searches in the dropdown | Issue: Voice input icon is not present in the search
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Navigate to the log in site 2. Hover on top of the search icon | 1. Navigate to the log in site 2. Click on the search icon 3. Check for recent searches | 1. Navigate to the log in site 2. Click on the search icon 3. Check for the voice search
Module: Search | Module: Search | Module: Search
Priority: Low | Priority: HIgh | Priority: HIgh
Screen Record: show nothing while hovering on search | Screenshot: Does not show recent searches | Screenshot: Missing voice input icon
Responsible QA: Amin Ocin | Responsible QA: Amin Ocin | Responsible QA: Amin Ocin